## UAT Test Plan
User Acceptance Test Plan
Project Name |  | Mortgage Montior
Testing Start Date / Time |  | 2024-06-07
Testing End Date / Time
Name of Tester/s: |  | Katherine Mulder
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
User management
1 | user can sign up | - Enter the username - Enter the password | Username: admin Password: admin.123 | Save the username and password into the database and direct the user to the login page after signing up. | Username and password saved into the database and login page displayed. | Pass | N/A
2 | user can log in | Enter the username. Enter the password. Click the sign-in button. | Username: admin Password: admin.123 | Show the idex page after login | Homepage displayed. | Pass | N/A
3 | user can update password | Click the "Update Password" button. | Username: admin New Password: admin.456 | Show a pop-up window for user input of a new password and update the database with the new password. | Update new password window displayed and the new password updated in the database. | Pass | N/A
4 | user can log out | Click on the logout button on the top right. | N/A | User logs out and the login page is displayed. | User logged out and login page appeared. | Pass | N/A
5 | User can remove account | Click the "Remove Account" button. | N/A | A checkbox appears to double-check for the removal of the account. | Checkbox appeared and account removed. | Pass | N/A
initial mortgage
1.1 | Mortgage name input | Enter the mortgage name in the input field. | Mortgage name: "Home Loan" | Form should accept the mortgage name as a text input. | Form collected the mortgage name correctly. | Pass | There is a bug that the override payment have to be input for both monthly and fornightly
1.2 | InitialiInterest rate input | Enter the initial interest rate in the input field. | Initial interest rate: 7% | Form should accept the initial interest rate as a numerical input and display it as a percentage. It should validate that the input is a number between 0 and 100. | Form collected and displayed the initial interest rate as a percentage correctly. | Pass | Although the data did nto change there was still a value error in the console. This error did not indicate if the fault was the sum of the numbers or that the input contained non numerical values.
1.3 | Initial term input | Enter the initial term in years in the input field. | Initial term: 30 years | Form should accept the initial term as a numerical input and validate that the input is a positive integer. It should display the term in years.The term should not more than 30 years | Form collected and displayed the initial term in years correctly. | Pass
1.4 | Initial principal input | Enter the initial principal amount in the input field. | Initial Principal: $1050,000 | Form should accept the initial principal as a numerical input and display it as a currency amount. It should validate that the input is a positive number. | Form collected and displayed the initial principal as a currency amount correctly. | Pass
1.5 | Deposit input | Enter the deposit amount in the input field. | Deposit: 50000 | Form should accept the deposit as a numerical input and display it as a currency amount. It should validate that the input is a positive number. | Form collected and displayed the deposit as a currency amount correctly. | Pass
1.6 | Extra costs input | Enter the extra costs amount in the input field. | Extra costs: 2000 | Form should accept the extra costs as a numerical input and display it as a currency amount. It should validate that the input is a positive number. | Form collected and displayed the extra costs as a currency amount correctly. | Pass
1.7 | Start date input | Enter the start date in the input field. | Start date: "30-06-2026" | Form should accept the start date as a date input and validate that the input follows the DD-MM-YYYY format. | Form collected and displayed the start date in the correct date format correctly. | Pass
1.8 | Comments input | Enter comments in the input field. | Comments: "the extra costs spent on the bank establishment fees" | Form should accept the comments as a text input. | Form collected and stored the comments correctly. | Pass
1.9 | Payment override enabled input | Select the boolean option for payment override. | Payment override enabled: True | Form should accept the boolean option and store it. | Form accepted and stored the payment override enabled option correctly. | Pass
1.1 | Monthly payment override input | Enter the monthly payment override amount if applicable. | Monthly payment override: 1200 | Form should accept the monthly payment override as a numerical input and display it as a currency amount. It should validate that the input is a positive number. | Form collected and displayed the monthly payment override amount as a currency amount correctly | Pass | Users must input both monthly and fortnightly override payments for the initial setup due to a bug
1.11 | Fortnightly payment override input | Enter the fortnightly payment override amount if applicable. | Fortnightly payment override: 600 | Form should accept the fortnightly payment override as a numerical input and display it as a currency amount. It should validate that the input is a positive number. | Form collected and displayed the fortnightly payment override amount as a currency amount correctly. | Pass | Users must input both monthly and fortnightly override payments for the initial setup due to a bug.
1.12 | Increment amounts input | Enter the increment amounts in the input field. | Increment amounts: 10000, 20000 | Form should accept the increment amounts as numerical inputs and display them as currency amounts. It should validate that the inputs are positive numbers. | Form collected and displayed the increment amounts as currency amounts correctly. | Pass
1.13 | Increment percentages input | Enter the increment percentages in the input field. | Increment percentages: 5 | Form should accept the increment percentages as numerical inputs and display them as percentages. It should validate that the inputs are numbers between 0 and 100. | Form collected and displayed the increment percentages as percentages correctly. | Pass
1.14 | Input validation | Implement input validation to ensure user inputs are correct and in the expected format. | Various test inputs as above | All user inputs should be validated for correctness and proper format. | All user inputs were validated successfully. | Pass
system process
2.1 | Validation of user inputs | Implement input validation to ensure user inputs are correct and in the expected format. Test each input field with valid and invalid data. | Valid data: "Home Loan", 3.5, 30, 250000, 50000, 2000, "2024-01-01", "First home purchase", True, 1200, 600, 10000, 20000, 5, 10 Invalid data: "", "abc", -1, "1000000abc", "20240101" | The system should validate all user inputs for correctness and format. Numerical inputs should be within acceptable ranges (e.g., positive numbers), text inputs should not contain invalid characters,invalid inputs should trigger appropriate error messages, preventing the user from proceeding until corrections are made. | All user inputs were validated successfully for correctness and proper format. Invalid inputs triggered appropriate error messages. | Pass | Users must input both monthly and fortnightly override payments for the initial setup due to a bug. If any field is left blank, the system breaks.
2.2 | Initial payment calculation | Create a function to calculate the initial monthly and fortnightly payments based on user inputs. | Principal: $840,000 Interest Rate: 5.0% Term: 30 years | The system should calculate the initial monthly payment as $4,509.30 and the fortnightly payment as $2,080.21. These results should match those of a standard financial calculator. | The system correctly calculated the initial monthly payment as $4,509.30 and the fortnightly payment as $2,080.21. | Pass
2.3 | Missing user input - initial interest rate | Leave the initial interest rate field blank and try to submit the form. | Initial Interest Rate: "" | The system should display an error message indicating that the initial interest rate is required and prevent the form submission. | The system breaks and does not display an appropriate error message. | Fail | The system breaks if the initial interest rate field is left blank.
2.4 | Missing user input - override payment only | Input only the monthly override payment and leave the fortnightly override payment field blank, and try to submit the form. | Monthly Payment Override: 1200, Fortnightly Payment Override: "" | The system should display an error message indicating that both override payments are required and prevent the form submission. | The system breaks and does not display an appropriate error message. | Fail | The system breaks if only one of the override payment fields is inputted.
2.5 | Mortgage maturity calculation | Calculate and store various maturity metrics for the mortgage based on user inputs. | Principal: $840,000 Interest Rate: 5.0% Term: 30 years Start Date: "30-06-2026" | The system should calculate and display the following metrics: Payments over full term: 360 months, Payments over reduced term: 138 months, Full term to amortize: 30 years, Estimated reduced term to amortize: 11 years and 6 months, Interest over full term: $782,565.09 ±0.1%, Principal + interest: $1,622,565.09, Interest over reduced term: $266,999.02 ±0.1%, Interest saved over reduced term: $516,349.57 ±0.1%, Principal + interest over reduced term: $1,106,999.02 | The system correctly calculated and displayed the various maturity metrics as expected. | Pass
2.6 | Amortization table generation | Generate the amortization schedule showing each payment, interest, principal reduction, and remaining balance. | Principal: $840,000 Interest Rate: 5.0% Term: 30 years. | The system should generate a detailed amortization table. The first entry should show a payment of $4,509.30, with $3,500.00 towards interest, $1,009.30 towards principal, and a remaining balance of $838,990.70. The final entry should show a remaining balance of $0.00. | The system correctly generated the amortization table with accurate details for each payment, interest, principal reduction, and remaining balance. | Pass
2.7 | Missing user input - term | Leave the term field blank and try to submit the form | Term: "" | The system should display an error message indicating that the term is required and prevent the form submission. | The system breaks and does not display an appropriate error message. | Fail | The system breaks if the term field is left blank.
2.8 | Projected payments calculation | Calculate projected monthly and fortnightly payments based on increment amounts and percentages | Principal: $840,000 Interest Rate: 5.0%, 7.0%, 9.0%, 11.0%, 13.0%, 15.0%, 17.0%, 19.0%, 21.0%, 23.0%, 25.0%, 27.0%, 29.0%, 31.0%, 33.0%, 35.0% Increment Amounts: $500 Increment Percentages: 2.0% | The system should calculate projected monthly payments for various principal increments and interest rates. For example, at 5.0% interest, a principal of $840,500 should have a monthly payment of $4,511.99, and at 7.0% interest, a principal of $840,500 should have a monthly payment of $5,591.87. | The system correctly calculated projected monthly payments for various principal increments and interest rates as expected. | Pass
2.9 | Graphical representations | Use Plotly to create visualizations of pprincipal and interest reduction. | Amortization data: monthly and mortnightly payment schedule for interest principal | Amortizationdispl monthly payment and fortnightly schedule | The system generated accurate and visually appealing graphs using Plotly, displaying all required details as expected. | Pass
General Questions/Comments